## Slide 1
Strategic Growth Partnership
A Proposal for DataFlow Analytics
Prepared by GrowthPath Consulting

## Slide 2
Understanding Your Challenge
We've listened. Here's what we heard:
• Rapid growth from 12 to 35 people has outpaced your processes • Knowledge lives in people's heads, not documented systems • New team member onboarding takes 12 weeks — far too long • Series B investors will scrutinise your operational maturity
"We're brilliant at solving our clients' data problems. We're terrible at solving our own operational ones."
— Marcus Chen, CEO

## Slide 3
The Cost of Inaction
Onboarding Delays
12 weeks
Every new hire takes 3 months to become productive. At your growth rate, that's significant lost capacity.
Knowledge Risk
Single Points
Critical knowledge exists only in key people's heads. One departure could halt operations.
Investor Scrutiny
Series B
Due diligence will expose operational gaps. Fix them now, or explain them later.

## Slide 4
Our Approach
A practical, phased methodology that builds lasting capability
1
Discover
Deep-dive into current operations, interview key stakeholders, map critical workflows
→
2
Design
Create scalable processes, define ownership, build documentation frameworks
→
3
Deliver
Implement changes alongside your team, train leaders, embed new ways of working
→
4
Sustain
Handover with full documentation, support transition, ensure independence

## Slide 5
What You'll Receive
Documentation
• 10 critical workflow playbooks
• Role and responsibility matrix
• Decision-making frameworks
• Onboarding programme (4-week)
Strategy
• 18-month strategic roadmap
• Prioritisation framework
• Series B narrative document
• Board deck refresh
Capability
• Leadership team coaching
• Process ownership training
• Change management support
• Quarterly review cadence

## Slide 6
Timeline and Milestones
Month 1
DISCOVER
Current State Report
Month 2
DESIGN
Process Blueprints
Month 3
DELIVER
First 5 Playbooks
Month 4
DELIVER
Leadership Training
Month 5
DELIVER
All 10 Playbooks
Month 6
SUSTAIN
Full Handover

## Slide 7
About GrowthPath
Growth Advisory for Scottish SMEs
We help ambitious Scottish businesses scale smart. Founded by operators who've been in your shoes, we bring practical experience — not theoretical frameworks.
Our approach is hands-on: we work alongside your team, building capability that lasts long after we leave. We measure success by your independence, not your dependency.
We understand the Scottish business ecosystem — the opportunities, the challenges, and the unique culture of doing business here.
By the Numbers
15+
Scottish SMEs advised
£12M
Client revenue growth
100%
Client retention rate

## Slide 8
Case Study: TechVenture Solutions
THE SITUATION
Edinburgh-based fintech, 28 employees, pre-Series A. Founder-led with no documented processes. New hires took 14 weeks to become productive. Investors flagged operational risk.
OUR APPROACH
5-month engagement: process mapping, playbook creation, leadership coaching, and Series A preparation. Worked alongside the team two days per week.
THE RESULTS
14 → 4 weeks
Onboarding time reduced by 71%
8 playbooks
Critical processes documented
£3.2M
Series A closed 3 months later
0 → 3
Promoted internal leaders
"GrowthPath didn't just give us documents — they built our management muscle. We closed our Series A three months ahead of schedule."
— Fiona MacLeod, CEO, TechVenture Solutions

## Slide 9
Investment
What's Included
• Full discovery and current state assessment
• 10 documented workflow playbooks
• Leadership team coaching sessions
• Onboarding programme redesign
• Series B narrative and board materials
• 6 months of hands-on support
Not Included
• Technology implementation (tools, software)
• Recruitment or HR services
• Legal or financial advisory
Total Investment
£45,000
6-month engagement
Monthly invoicing: £7,500/month.
50% payable on signing,
balance monthly.

## Slide 10
Next Steps
1
Review this proposal with your team
2
Schedule a follow-up call to discuss questions
3
Sign engagement letter and begin Discovery
Ready to talk?
hodl@growthpath.scot